## Automation Matrix
Automation ID | Automation / Check | Assessment Domain | Implementation Approach | Primary SAP Objects | Developer Activities | Recommended Technology | Ease of Implementation (1-5) | Customer Acceptance (1-5) | Customer Risk (1-5) | Business Value (1-5) | Automation Potential (%) | Requires Custom ABAP? | Requires Transport? | Read Only? | ECC Supported | S/4 Supported | RISE/ECS Supported | Estimated Dev Effort (Days) | Recommended Output | Notes
AUTO-001 | Landscape Discovery | Landscape | Read CVERS/System Status | CVERS | Build PyRFC collector | Python + PyRFC | 5 | 5 | 1 | 5 | 95 | No | No | Yes | Yes | Yes | Partial | 2 | System inventory | Low risk
AUTO-002 | Dormant User Analysis | Users | Read user master | USR02 | Inactive user logic | Python + PyRFC | 5 | 5 | 1 | 5 | 95 | No | No | Yes | Yes | Yes | Yes | 2 | Dormant user report | Configurable threshold
AUTO-003 | Standard User Review | Users | Read SAP*, DDIC | USR02 | Status validation | Python + PyRFC | 5 | 5 | 1 | 5 | 100 | No | No | Yes | Yes | Yes | Yes | 1 | Critical account report
AUTO-004 | Role Hierarchy Analysis | Roles | Analyze AGR tables | AGR_DEFINE, AGR_AGRS | Role parser | Python | 5 | 5 | 1 | 5 | 95 | No | No | Yes | Yes | Yes | Yes | 4 | Hierarchy report
AUTO-005 | Critical Authorization Scan | Roles | Analyze role auths | AGR_1251 | Risk rules engine | Python | 5 | 5 | 1 | 5 | 95 | No | No | Yes | Yes | Yes | Yes | 5 | Critical access matrix
AUTO-006 | Profile Parameter Review | System | Compare against baseline | RSPARAM | Baseline comparison | Python | 4 | 5 | 1 | 5 | 90 | No | No | Yes | Yes | Yes | Partial | 5 | Compliance report | Maintain baseline library
AUTO-007 | RFC Security Assessment | Interfaces | Read SM59 | RFCDES | RFC parser | Python | 4 | 4 | 2 | 4 | 90 | No | No | Yes | Yes | Yes | Yes | 4 | RFC inventory
AUTO-008 | Gateway ACL Review | Interfaces | Read reginfo/secinfo | Gateway ACL | ACL parser | Python/ABAP | 3 | 3 | 2 | 4 | 75 | Optional | No | Yes | Yes | Yes | Partial | 6 | Gateway report | May need BASIS
AUTO-009 | Firefighter Analysis | GRC | Read GRC tables | GRACFF* | Collector | Python | 4 | 4 | 1 | 4 | 85 | No | No | Yes | Yes | Yes | N/A | 4 | FF dashboard | Requires GRC auth
AUTO-010 | Fiori Exposure | Fiori | Read SICF/OData | SICF,/IWFND | Service inventory | Python | 4 | 4 | 1 | 4 | 90 | No | No | Yes | Yes | Yes | Yes | 3 | Exposure report
AUTO-011 | Security Notes Readiness | Patching | Compare versions | CVERS | External baseline | Python + API | 2 | 3 | 1 | 5 | 60 | No | No | Yes | Yes | Yes | Yes | 8 | Patch readiness | Needs SAP note catalog

## Ranking Criteria
Metric | Score 1 | Score 3 | Score 5
Ease of Implementation | Complex custom solution | Moderate effort | Standard RFC/table read
Customer Acceptance | Major concerns | Needs discussion | Read-only, non-invasive
Customer Risk | High operational risk | Limited risk | Negligible risk
Business Value | Low | Medium | High customer impact

## Developer Stack
Component | Recommendation | Purpose
Language | Python | Core assessment engine
SAP Connectivity | PyRFC | Read SAP data
Alternative | Custom ABAP RFC | Restricted landscapes
Reporting | openpyxl | Excel reports
Database | SQLite/PostgreSQL | Assessment history
AI | LLM | Summaries & remediation
Version Control | Git | Source management
Packaging | PyInstaller | Desktop executable

## Implementation Roadmap
Phase | Objective | Deliverables
Phase 1 | SAP Connectivity | PyRFC, authentication
Phase 2 | Collector Framework | Generic collectors
Phase 3 | Assessment Rules | Baseline engine
Phase 4 | Risk Scoring | Maturity & risk scoring
Phase 5 | AI Reporting | Executive report generation
Phase 6 | Packaging | Installer & configuration