## README
Security Framework Assessment & Transformation Readiness
Project Tracker Pack — Daily Task Tracker ¦ Prerequisite Checklist ¦ SAP Security SME Questionnaire ¦ Summary Dashboard
How to use this workbook
1. 'Daily Task Tracker' lays out the build plan day-by-day from kickoff to production handover.
2. 'Prerequisite Checklist' lists everything to secure (access, approvals, infra) before collectors run on any system.
3. 'SME Questionnaire' is what to walk through with the SAP Security SME(s) — internal and, later, per customer.
4. 'Summary Dashboard' auto-rolls up workload and completion status from the other sheets — nothing to fill in there.
5. Update the Project Start Date below — the Date column on the Daily Task Tracker recalculates automatically (skips weekends).
6. Status, Priority, and Owner cells use dropdowns (data validation) — click the cell and choose from the list.
Project Start Date (input) | 2026-07-13
Team & Assumed Roles
Note: you confirmed Rohan and Shweta. The plan below assumes a 3rd (SAP Security SME) and 4th (Business/Consulting Lead) seat based on the roles in your reference document — rename these in the Owner columns once confirmed; the structure of the plan does not otherwise change.
Owner Label Used In Sheets | Assumed Role | Primary Responsibility in This Plan
Rohan | Project Lead / Developer | Architecture, scoring engine, baseline library, ECS/RISE boundary logic, SME coordination
Shweta | Developer | Collector scripts, AI/report generation layer, testing, environment setup
SAP Security SME | SAP Security Subject Matter Expert | Baseline validation, technical accuracy review, mandatory sign-off before customer delivery
Business/Consulting Lead | Sales / Consulting Lead | Customer coordination, access requests, commercial packaging, pilot logistics
Timeline assumption
~9 working weeks (43 working days) from kickoff to production handover, with a 2-person build team, 1 SME, and 1 business/consulting lead running in parallel. Adjust pace in the Daily Task Tracker if your team's availability differs (e.g. part-time SME).

## Daily Task Tracker
Day | Date | Week | Phase | Task | Subtask | Owner | Est. Hours | Status | Dependencies | Deliverable | Comments
1 | 2026-07-13 | 1 | Phase 0 - Discovery & SME Alignment | Project Kickoff & Scope Alignment | Kickoff meeting - align scope, success criteria, timeline, RACI | Rohan | 2 | Not Started | None | Signed-off scope note | All 4 attend
1 | 2026-07-13 | 1 | Phase 0 - Discovery & SME Alignment | Project Kickoff & Scope Alignment | Review prior SAP security assessment collateral & this reference doc | Rohan | 2 | Not Started | None | Discovery notes v0
1 | 2026-07-13 | 1 | Phase 0 - Discovery & SME Alignment | Project Kickoff & Scope Alignment | Set up project workspace - shared drive, board (Jira/Trello), Git repo | Shweta | 3 | Not Started | None | Project workspace live
1 | 2026-07-13 | 1 | Phase 0 - Discovery & SME Alignment | Project Kickoff & Scope Alignment | Draft SME questionnaire distribution list & interview schedule | Business/Consulting Lead | 2 | Not Started | None | Interview schedule | Book SME calendar early
2 | 2026-07-14 | 1 | Phase 0 - Discovery & SME Alignment | SME Questionnaire Kickoff | Finalize and circulate SME Questionnaire v1 to internal SME | Rohan | 2 | Not Started | Day 1 kickoff | SME Questionnaire sent
2 | 2026-07-14 | 1 | Phase 0 - Discovery & SME Alignment | SME Questionnaire Kickoff | Research RISE/ECS responsibility matrix (SAP contract docs, OSS notes) | Rohan | 3 | Not Started | None | ECS boundary notes v0 | Critical for scoring model
2 | 2026-07-14 | 1 | Phase 0 - Discovery & SME Alignment | SME Questionnaire Kickoff | Set up Python dev environment - repo scaffold, linting, CI skeleton | Shweta | 4 | Not Started | Workspace live | Dev environment ready
2 | 2026-07-14 | 1 | Phase 0 - Discovery & SME Alignment | SME Questionnaire Kickoff | Confirm SME availability windows for interviews (Days 3-5) | Business/Consulting Lead | 1 | Not Started | Interview schedule | Confirmed calendar invites
3 | 2026-07-15 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #1 - Auth Concept & Role Design | SME interview - authorization concept, role design standards, naming conventions | Rohan | 2 | Not Started | SME available | Interview notes - Auth Concept | SME co-attends
3 | 2026-07-15 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #1 - Auth Concept & Role Design | Research SAP security baseline standards (SAP Security Baseline, DSAG, BSI) | Shweta | 3 | Not Started | None | Baseline research pack
3 | 2026-07-15 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #1 - Auth Concept & Role Design | Document RISE/ECS boundary rules per technical domain (params/RFC/gateway) | Rohan | 2 | Not Started | ECS boundary notes v0 | ECS boundary matrix v1 | Key risk item from brief
3 | 2026-07-15 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #1 - Auth Concept & Role Design | Draft initial data source inventory (tables/tcodes/reports needed) | Shweta | 2 | Not Started | Baseline research pack | Data source inventory v0 | AGR_*, USR*, TSTC, RSPARAM etc.
4 | 2026-07-16 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #2 - RFC, Gateway & Critical Auths | SME interview - RFC destination hardening, gateway ACLs, critical basis auths | Rohan | 2 | Not Started | Day 3 notes | Interview notes - RFC/Gateway
4 | 2026-07-16 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #2 - RFC, Gateway & Critical Auths | Define read-only technical user + authorization profile for collectors | Shweta | 3 | Not Started | Data source inventory v0 | Technical user auth spec v0 | Feeds Prerequisite Checklist
4 | 2026-07-16 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #2 - RFC, Gateway & Critical Auths | Draft prerequisite access request template for customer Basis team | Business/Consulting Lead | 2 | Not Started | Technical user auth spec v0 | Access request template
4 | 2026-07-16 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #2 - RFC, Gateway & Critical Auths | Consolidate Day 1-4 findings into discovery notes | Rohan | 1 | Not Started | All prior interviews | Discovery notes v1
5 | 2026-07-17 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #3 - SoD, GRC, Interfaces + Week 1 Close | SME interview - SoD ruleset, GRC maturity, Fiori/OData, transport process | Rohan | 2 | Not Started | Day 4 notes | Interview notes - SoD/GRC/Interfaces
5 | 2026-07-17 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #3 - SoD, GRC, Interfaces + Week 1 Close | Finalize Prerequisite Checklist v1 (draft) | Shweta | 3 | Not Started | Technical user auth spec v0 | Prerequisite Checklist v1
5 | 2026-07-17 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #3 - SoD, GRC, Interfaces + Week 1 Close | Finalize SME Questionnaire v1 - fold in internal SME feedback | Rohan | 2 | Not Started | SME Questionnaire sent | SME Questionnaire v1 (final)
5 | 2026-07-17 | 1 | Phase 0 - Discovery & SME Alignment | SME Interview #3 - SoD, GRC, Interfaces + Week 1 Close | Week 1 retro & Week 2 planning | Rohan | 1 | Not Started | None | Week 2 plan | All 4 attend
6 | 2026-07-20 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Baseline Library Structure | Design baseline library schema (YAML/JSON) - one entry per control | Shweta | 4 | Not Started | Baseline research pack | Baseline schema v0
6 | 2026-07-20 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Baseline Library Structure | Define control categories: auth concept, params, RFC, gateway, critical auths, interfaces, SoD | Rohan | 3 | Not Started | Baseline schema v0 | Control taxonomy v1
6 | 2026-07-20 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Baseline Library Structure | Map SAP-recommended baseline values (login/password policy, auth switches, etc.) | Rohan | 3 | Not Started | Control taxonomy v1 | Baseline values v0 | SME to validate Day 7
6 | 2026-07-20 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Baseline Library Structure | Tag ECS/RISE ownership flag against each baseline entry | Rohan | 2 | Not Started | ECS boundary matrix v1 | Baseline entries flagged | Ties to key risk in brief
7 | 2026-07-21 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Scoring Model Design | Define maturity model (0-5 levels) per control category | Rohan | 3 | Not Started | Control taxonomy v1 | Maturity model v1
7 | 2026-07-21 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Scoring Model Design | Define weighting/scoring algorithm (control criticality x compliance gap) | Shweta | 3 | Not Started | Maturity model v1 | Scoring algorithm spec v0
7 | 2026-07-21 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Scoring Model Design | Design transformation readiness dimensions (auth complexity, custom code, interfaces) | Rohan | 3 | Not Started | Maturity model v1 | Readiness scoring spec v0
7 | 2026-07-21 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Scoring Model Design | SME review of maturity levels for technical accuracy | SAP Security SME | 2 | Not Started | Maturity model v1 | SME feedback log | Mandatory review gate
8 | 2026-07-22 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Collector Scope Definition | Finalize RFC-enabled function modules / read APIs needed per data source | Shweta | 3 | Not Started | Data source inventory v0 | Collector API list v1
8 | 2026-07-22 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Collector Scope Definition | Validate read-only sufficiency of each API with SME (no execute risk) | SAP Security SME | 2 | Not Started | Collector API list v1 | Read-only validation sign-off | Guardrail: read-only only
8 | 2026-07-22 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Collector Scope Definition | Draft collector script architecture - modular per security domain | Rohan | 3 | Not Started | Collector API list v1 | Collector architecture v1
8 | 2026-07-22 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Collector Scope Definition | Define collector output JSON schema | Shweta | 2 | Not Started | Collector architecture v1 | Collector output schema v1
9 | 2026-07-23 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Reporting & Roadmap Design | Design LLM prompt templates for findings narrative generation | Rohan | 3 | Not Started | Scoring algorithm spec v0 | Prompt templates v0
9 | 2026-07-23 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Reporting & Roadmap Design | Define report structure - exec summary, technical findings, gap analysis, roadmap | Rohan | 2 | Not Started | Prompt templates v0 | Report structure spec v1
9 | 2026-07-23 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Reporting & Roadmap Design | Draft remediation prioritization logic (risk x effort matrix) | Shweta | 3 | Not Started | Readiness scoring spec v0 | Prioritization logic v0
9 | 2026-07-23 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Reporting & Roadmap Design | Draft customer-facing roadmap deck template outline | Business/Consulting Lead | 2 | Not Started | Report structure spec v1 | Deck outline v0
10 | 2026-07-24 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Design Review & Sign-off (Week 2 Close) | Internal design review - architecture, scoring model, baseline library | Rohan | 2 | Not Started | All Week 2 outputs | Design review notes | All 4 attend
10 | 2026-07-24 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Design Review & Sign-off (Week 2 Close) | SME sign-off on Baseline Library v1 | SAP Security SME | 2 | Not Started | Baseline entries flagged | Baseline Library v1 (signed off) | Version-controlled per guardrail
10 | 2026-07-24 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Design Review & Sign-off (Week 2 Close) | Finalize Prerequisite Checklist v2 with access/API findings | Shweta | 2 | Not Started | Collector API list v1 | Prerequisite Checklist v2
10 | 2026-07-24 | 2 | Phase 1 - Baseline Library & Scoring Model Design | Design Review & Sign-off (Week 2 Close) | Week 2 retro & Week 3 planning | Rohan | 1 | Not Started | None | Week 3 plan
11 | 2026-07-27 | 3 | Phase 2 - Collector Script Development | Auth Concept Collector - Build | Build collector: AGR_* tables, role/profile assignments | Shweta | 4 | Not Started | Collector architecture v1 | Collector: Auth Concept v0.1
11 | 2026-07-27 | 3 | Phase 2 - Collector Script Development | Auth Concept Collector - Build | Build SUIM extraction scripts - user/role listing, critical combos | Rohan | 4 | Not Started | Collector architecture v1 | Collector: SUIM extract v0.1
12 | 2026-07-28 | 3 | Phase 2 - Collector Script Development | Auth Concept Collector - Depth | Parse role naming convention adherence, single vs composite vs derived | Shweta | 3 | Not Started | Collector: Auth Concept v0.1 | Role hygiene parser v0.1
12 | 2026-07-28 | 3 | Phase 2 - Collector Script Development | Auth Concept Collector - Depth | Build SoD data extraction logic (via SUIM, or GRC export if available) | Rohan | 4 | Not Started | Collector: SUIM extract v0.1 | SoD data extractor v0.1
13 | 2026-07-29 | 3 | Phase 2 - Collector Script Development | Profile Parameter Collector | Build RSPARAM/profile parameter extraction script | Shweta | 4 | Not Started | Collector output schema v1 | Collector: Profile Params v0.1
13 | 2026-07-29 | 3 | Phase 2 - Collector Script Development | Profile Parameter Collector | Map extracted parameters against Baseline Library thresholds | Rohan | 3 | Not Started | Baseline Library v1 (signed off) | Parameter comparison logic v0.1
14 | 2026-07-30 | 3 | Phase 2 - Collector Script Development | RFC & Gateway Collector | Build SM59 RFC destination extraction (type, auth method, stored creds flag) | Shweta | 4 | Not Started | Read-only validation sign-off | Collector: RFC Destinations v0.1
14 | 2026-07-30 | 3 | Phase 2 - Collector Script Development | RFC & Gateway Collector | Build gateway ACL parser (secinfo/reginfo) | Rohan | 4 | Not Started | Read-only validation sign-off | Collector: Gateway ACL v0.1
15 | 2026-07-31 | 3 | Phase 2 - Collector Script Development | Critical Basis Auths & Standard Users Collector | Build critical authorization check (SAP_ALL/SAP_NEW, S_TABU_DIS, S_DEVELOP etc.) | Shweta | 4 | Not Started | Collector: Auth Concept v0.1 | Collector: Critical Auths v0.1
15 | 2026-07-31 | 3 | Phase 2 - Collector Script Development | Critical Basis Auths & Standard Users Collector | Build standard user status check (SAP*, DDIC, EARLYWATCH, TMSADM) | Rohan | 3 | Not Started | Collector output schema v1 | Collector: Standard Users v0.1
16 | 2026-08-03 | 4 | Phase 2 - Collector Script Development | Security Switch & Audit Log Collector | Build RZ11 security switch extraction (login/password policy, auth switches) | Shweta | 3 | Not Started | Collector: Profile Params v0.1 | Collector: RZ11 Switches v0.1
16 | 2026-08-03 | 4 | Phase 2 - Collector Script Development | Security Switch & Audit Log Collector | Build SM19/SM20 audit log configuration check | Rohan | 3 | Not Started | Collector output schema v1 | Collector: Audit Log Config v0.1
17 | 2026-08-04 | 4 | Phase 2 - Collector Script Development | Interface / Fiori / OData Collector | Build SICF service status extraction (active/inactive, auth checks) | Shweta | 4 | Not Started | Collector output schema v1 | Collector: SICF Services v0.1
17 | 2026-08-04 | 4 | Phase 2 - Collector Script Development | Interface / Fiori / OData Collector | Build OData/Fiori service security check | Rohan | 4 | Not Started | Collector: SICF Services v0.1 | Collector: OData Security v0.1
18 | 2026-08-05 | 4 | Phase 2 - Collector Script Development | Collector Integration & Error Handling | Integrate all collector modules into a single agentless runner | Shweta | 5 | Not Started | All collector modules v0.1 | Unified collector runner v0.1
18 | 2026-08-05 | 4 | Phase 2 - Collector Script Development | Collector Integration & Error Handling | Add error handling, retry logic, and structured logging | Rohan | 4 | Not Started | Unified collector runner v0.1 | Collector runner v0.2 (hardened)
19 | 2026-08-06 | 4 | Phase 2 - Collector Script Development | Collector Testing Round 1 | Unit test each collector module against internal test system | Shweta | 4 | Not Started | Collector runner v0.2 | Unit test results - Round 1
19 | 2026-08-06 | 4 | Phase 2 - Collector Script Development | Collector Testing Round 1 | Cross-check sample collector output field-by-field | Rohan | 3 | Not Started | Unit test results - Round 1 | QA notes - Round 1
19 | 2026-08-06 | 4 | Phase 2 - Collector Script Development | Collector Testing Round 1 | SME review of sample collector output for accuracy/completeness | SAP Security SME | 2 | Not Started | QA notes - Round 1 | SME review notes - Collectors | Mandatory review gate
20 | 2026-08-07 | 4 | Phase 2 - Collector Script Development | Collector Refinement & Sign-off (Week 3-4 Close) | Fix issues identified in Day 19 SME/QA review | Shweta | 4 | Not Started | SME review notes - Collectors | Collector runner v1.0
20 | 2026-08-07 | 4 | Phase 2 - Collector Script Development | Collector Refinement & Sign-off (Week 3-4 Close) | Re-validate fixes against test system | Rohan | 3 | Not Started | Collector runner v1.0 | Regression check - Collectors
20 | 2026-08-07 | 4 | Phase 2 - Collector Script Development | Collector Refinement & Sign-off (Week 3-4 Close) | Sign-off on Collector Pack v1.0; tag in version control | Rohan | 1 | Not Started | Regression check - Collectors | Collector Pack v1.0 (tagged) | All 4 sign off
21 | 2026-08-10 | 5 | Phase 3 - Scoring Engine Development | Scoring Engine Core | Build scoring engine ingesting collector JSON output | Shweta | 4 | Not Started | Collector Pack v1.0 | Scoring engine core v0.1
21 | 2026-08-10 | 5 | Phase 3 - Scoring Engine Development | Scoring Engine Core | Implement baseline comparison logic (current vs. Baseline Library) | Rohan | 4 | Not Started | Baseline Library v1 (signed off) | Baseline comparison module v0.1
22 | 2026-08-11 | 5 | Phase 3 - Scoring Engine Development | Maturity & Readiness Scoring | Implement maturity score calculation per control category | Shweta | 4 | Not Started | Scoring engine core v0.1 | Maturity scoring module v0.1
22 | 2026-08-11 | 5 | Phase 3 - Scoring Engine Development | Maturity & Readiness Scoring | Implement transformation readiness score calculation | Rohan | 4 | Not Started | Readiness scoring spec v0.0 | Readiness scoring module v0.1
23 | 2026-08-12 | 5 | Phase 3 - Scoring Engine Development | ECS / RISE Boundary Logic | Implement ECS/RISE flag - exclude SAP-managed items from customer risk score | Shweta | 4 | Not Started | Baseline entries flagged | ECS boundary logic v0.1 | Directly addresses brief's key risk
23 | 2026-08-12 | 5 | Phase 3 - Scoring Engine Development | ECS / RISE Boundary Logic | Validate ECS boundary logic against RISE responsibility matrix | SAP Security SME | 3 | Not Started | ECS boundary logic v0.1 | ECS boundary validation sign-off | Mandatory review gate
24 | 2026-08-13 | 5 | Phase 3 - Scoring Engine Development | Gap Analysis & Prioritization | Build gap analysis output (current state vs. baseline, by category) | Shweta | 4 | Not Started | Baseline comparison module v0.1 | Gap analysis module v0.1
24 | 2026-08-13 | 5 | Phase 3 - Scoring Engine Development | Gap Analysis & Prioritization | Build remediation prioritization logic (risk x effort matrix) | Rohan | 4 | Not Started | Prioritization logic v0.0 | Prioritization module v0.1
25 | 2026-08-14 | 5 | Phase 3 - Scoring Engine Development | Scoring Engine Testing & Sign-off | Test scoring engine end-to-end against sample dataset | Shweta | 4 | Not Started | All scoring modules v0.1 | Scoring engine test results
25 | 2026-08-14 | 5 | Phase 3 - Scoring Engine Development | Scoring Engine Testing & Sign-off | Review scoring outputs for logical soundness / edge cases (zero findings, all-critical) | Rohan | 3 | Not Started | Scoring engine test results | Scoring QA notes
25 | 2026-08-14 | 5 | Phase 3 - Scoring Engine Development | Scoring Engine Testing & Sign-off | SME review of scoring outputs for technical soundness | SAP Security SME | 2 | Not Started | Scoring QA notes | Scoring Engine v1.0 (signed off) | Mandatory review gate
26 | 2026-08-17 | 6 | Phase 4 - AI Reporting & Roadmap Layer | LLM Integration Setup | Set up LLM API integration - prompt assembly + context injection from scored data | Shweta | 4 | Not Started | Scoring Engine v1.0 | LLM integration v0.1
26 | 2026-08-17 | 6 | Phase 4 - AI Reporting & Roadmap Layer | LLM Integration Setup | Draft and test executive summary prompt template | Rohan | 3 | Not Started | Prompt templates v0.0 | Exec summary prompt v0.1
27 | 2026-08-18 | 6 | Phase 4 - AI Reporting & Roadmap Layer | Findings Report Generation | Build automated technical findings report generator | Shweta | 4 | Not Started | LLM integration v0.1 | Findings report generator v0.1
27 | 2026-08-18 | 6 | Phase 4 - AI Reporting & Roadmap Layer | Findings Report Generation | Build gap analysis narrative section generator | Rohan | 3 | Not Started | Gap analysis module v0.1 | Gap narrative generator v0.1
28 | 2026-08-19 | 6 | Phase 4 - AI Reporting & Roadmap Layer | Remediation Roadmap Deck Generation | Build PPT roadmap deck generator (python-pptx) from prioritization output | Shweta | 5 | Not Started | Prioritization module v0.1 | Roadmap deck generator v0.1
28 | 2026-08-19 | 6 | Phase 4 - AI Reporting & Roadmap Layer | Remediation Roadmap Deck Generation | Design roadmap slide template - phased remediation plan, cost/effort view | Business/Consulting Lead | 3 | Not Started | Deck outline v0.0 | Roadmap slide template v1
29 | 2026-08-20 | 6 | Phase 4 - AI Reporting & Roadmap Layer | Report Formatting, Branding & QA | Apply firm branding/template to generated reports and deck | Business/Consulting Lead | 3 | Not Started | Roadmap slide template v1 | Branded report templates
29 | 2026-08-20 | 6 | Phase 4 - AI Reporting & Roadmap Layer | Report Formatting, Branding & QA | QA pass on generated report language, tone, and factual consistency | Rohan | 3 | Not Started | Findings report generator v0.1 | Report QA notes
30 | 2026-08-21 | 6 | Phase 4 - AI Reporting & Roadmap Layer | AI Layer End-to-End Testing | Test end-to-end report generation on sample scored dataset | Shweta | 4 | Not Started | Branded report templates | E2E report test - Round 1
30 | 2026-08-21 | 6 | Phase 4 - AI Reporting & Roadmap Layer | AI Layer End-to-End Testing | Full pipeline dry run: collector -> scoring -> report -> deck | Rohan | 3 | Not Started | E2E report test - Round 1 | Pipeline dry-run notes
30 | 2026-08-21 | 6 | Phase 4 - AI Reporting & Roadmap Layer | AI Layer End-to-End Testing | SME review of AI-generated findings for accuracy | SAP Security SME | 3 | Not Started | Pipeline dry-run notes | SME review notes - AI Layer | Mandatory review gate
31 | 2026-08-24 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Unit & Integration Testing | Complete unit test suite for collectors + scoring engine | Shweta | 4 | Not Started | Collector Pack v1.0 / Scoring Engine v1.0 | Unit test suite complete
31 | 2026-08-24 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Unit & Integration Testing | Integration testing across full pipeline (collector to report) | Rohan | 4 | Not Started | Unit test suite complete | Integration test results
32 | 2026-08-25 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Security Testing | Verify collectors are strictly read-only - no write/execute exposure | Rohan | 3 | Not Started | Integration test results | Read-only verification report | Guardrail per brief
32 | 2026-08-25 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Security Testing | Validate technical user authorization scope - least-privilege check | SAP Security SME | 3 | Not Started | Read-only verification report | Least-privilege sign-off | Mandatory review gate
33 | 2026-08-26 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Performance Testing | Run collectors against a larger test system - measure runtime and load impact | Shweta | 4 | Not Started | Integration test results | Performance test report
33 | 2026-08-26 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Performance Testing | Confirm no measurable performance degradation on target SAP system | Rohan | 2 | Not Started | Performance test report | Performance sign-off
34 | 2026-08-27 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Full Dry-Run & SME UAT Round 1 | Full dry-run assessment on internal test system, start to finish | Rohan | 4 | Not Started | All Phase 5 sign-offs | Dry-run report + deck (draft) | All 4 observe/participate
34 | 2026-08-27 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Full Dry-Run & SME UAT Round 1 | SME reviews full report and roadmap deck for technical accuracy | SAP Security SME | 3 | Not Started | Dry-run report + deck (draft) | UAT Round 1 findings log | Mandatory review gate
35 | 2026-08-28 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Defect Fixing & Baseline Tuning | Fix issues identified in UAT Round 1 | Shweta | 4 | Not Started | UAT Round 1 findings log | Defect fix log
35 | 2026-08-28 | 7 | Phase 5 - Testing (Unit/Integration/Security) | Defect Fixing & Baseline Tuning | Update Baseline Library / scoring logic per SME feedback | Rohan | 3 | Not Started | UAT Round 1 findings log | Baseline Library v1.1
36 | 2026-08-31 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Preparation | Select pilot customer/system and confirm scope with sponsor | Business/Consulting Lead | 3 | Not Started | Baseline Library v1.1 | Pilot scope confirmed
36 | 2026-08-31 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Preparation | Prepare Prerequisite Checklist and access request pack for pilot customer | Business/Consulting Lead | 3 | Not Started | Prerequisite Checklist v2 | Pilot access request pack
37 | 2026-09-01 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Access & Setup | Obtain customer approvals and provision read-only technical user | Business/Consulting Lead | 3 | Not Started | Pilot access request pack | Pilot technical user provisioned | Depends on customer Basis team
37 | 2026-09-01 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Access & Setup | Deploy collector package to pilot landscape via secure channel | Shweta | 3 | Not Started | Pilot technical user provisioned | Collector deployed - pilot
38 | 2026-09-02 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Execution | Run collectors on pilot system | Rohan | 3 | Not Started | Collector deployed - pilot | Pilot raw data captured
38 | 2026-09-02 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Execution | Run collectors - second pass / edge cases (multiple clients, systems) | Shweta | 3 | Not Started | Pilot raw data captured | Pilot raw data - full landscape
38 | 2026-09-02 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Execution | Validate data completeness against expected data source inventory | SAP Security SME | 2 | Not Started | Pilot raw data - full landscape | Data completeness sign-off
39 | 2026-09-03 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Report Generation & Mandatory SME Review | Generate scored findings report + roadmap deck for pilot customer | Shweta | 3 | Not Started | Data completeness sign-off | Pilot report + deck (draft)
39 | 2026-09-03 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Report Generation & Mandatory SME Review | SME review before customer delivery (mandatory gate per guardrails) | SAP Security SME | 3 | Not Started | Pilot report + deck (draft) | Pilot report + deck (SME-approved) | Non-negotiable guardrail from brief
40 | 2026-09-04 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Feedback & Iteration (Week 8 Close) | Internal pilot retrospective - capture lessons learned | Rohan | 2 | Not Started | Pilot report + deck (SME-approved) | Pilot retro notes | All 4 attend
40 | 2026-09-04 | 8 | Phase 6 - Pilot Run & Refinement | Pilot Feedback & Iteration (Week 8 Close) | Refine Baseline Library / scoring / report templates based on pilot | Shweta | 4 | Not Started | Pilot retro notes | Baseline Library v1.2 / Report templates v1.1
41 | 2026-09-07 | 9 | Phase 7 - Productionization & Handover | Documentation | Write operator documentation - runbook, troubleshooting guide | Rohan | 4 | Not Started | Collector Pack v1.0+ | Operator runbook v1
41 | 2026-09-07 | 9 | Phase 7 - Productionization & Handover | Documentation | Document Baseline Library versioning and change process | Shweta | 3 | Not Started | Baseline Library v1.2 | Baseline versioning SOP
42 | 2026-09-08 | 9 | Phase 7 - Productionization & Handover | Commercial Packaging | Finalize business proposal / pricing and engagement model | Business/Consulting Lead | 4 | Not Started | Pilot retro notes | Business proposal v1
42 | 2026-09-08 | 9 | Phase 7 - Productionization & Handover | Commercial Packaging | Finalize customer-facing pitch deck using pilot outcomes as proof point | Business/Consulting Lead | 4 | Not Started | Pilot report + deck (SME-approved) | Customer pitch deck v1
43 | 2026-09-09 | 9 | Phase 7 - Productionization & Handover | Go-Live Readiness Review | Final go/no-go review across scope, quality, guardrails | Rohan | 2 | Not Started | All Phase 6-7 deliverables | Go-live decision | All 4 sign off
43 | 2026-09-09 | 9 | Phase 7 - Productionization & Handover | Go-Live Readiness Review | Tag Collector + Scoring + Baseline Library as v1.0 production release | Shweta | 2 | Not Started | Go-live decision | Production release v1.0 (tagged) | Version-controlled per guardrail
Formulas:
Date = WORKDAY(README!$C13-1,[Day])

## Prerequisite Checklist
# | Category | Checklist Item | Description / Requirement | Required From | Priority | Status | Owner | Notes
1 | SAP System Access | Test/sandbox SAP system available (ECC or S/4) | Non-production system for internal dev and collector testing, not an empty client | Internal IT/Basis | High | Not Started | Rohan
2 | SAP System Access | Representative test system with real-ish data | Populated roles, RFCs, parameters - not a vanilla client - so collectors have something meaningful to read | Internal IT/Basis | High | Not Started | Rohan
3 | SAP System Access | Dedicated technical/communication user created | Read-only, S_RFC-based communication user for collector to log on as | Internal Basis Team | High | Not Started | Shweta
4 | SAP System Access | Remote connectivity to test system configured | VPN/SAProuter access from collector host to the SAP application server | Internal IT | Medium | Not Started | Shweta
5 | Authorizations | Least-privilege auth profile for technical user | Display-only auth objects: S_TABU_DIS (display), S_RFC, S_USER_GRP (display), S_TCODE for SUIM/SM59/RZ11 (display) | Internal Basis/SME | High | Not Started | SAP Security SME
6 | Authorizations | Confirm no write/execute rights on collector user | No S_TABU_DIS write, no RFC test-connection execute, no BAPI execute beyond the approved read list | SAP Security SME | High | Not Started | SAP Security SME
7 | Authorizations | Written least-privilege confirmation on file | Signed note from SME/Basis confirming the technical user's authorization scope before first run | SAP Security SME | High | Not Started | SAP Security SME
8 | Data Sources | Finalized table read list confirmed accessible | AGR_*, USR*, UST*, TSTC, TSTCT, TOBJ, USOBT_C, USOBX_C - confirm technical user can read each | SAP Security SME | High | Not Started | Shweta
9 | Data Sources | Finalized transaction/report list confirmed accessible | SUIM, RZ10, RZ11, SM59, SICF, SM20/RSAU - confirm display access | SAP Security SME | High | Not Started | Shweta
10 | Data Sources | Table read method decided (RFC_READ_TABLE vs custom Z-RFC) | Decide and document; if a custom Z-RFC is required, treat as a build dependency | Rohan / SAP Security SME | High | Not Started | Rohan
11 | Data Sources | Transport request raised for any custom Z-RFC | If a Z-RFC module is required for read access, get it built, tested, and transported | Basis/Transport Team | Medium | Not Started | Shweta
12 | RFC / Gateway | List of RFC destinations to inspect confirmed (SM59) | Scope which RFC destinations are in-bounds for the assessment | SAP Security SME | Medium | Not Started | Rohan
13 | RFC / Gateway | Gateway ACL file location and read access confirmed | secinfo/reginfo file paths and read permissions verified for the collector host | Internal Basis Team | Medium | Not Started | Rohan
14 | Infrastructure | Python environment provisioned on collector host | Correct Python version plus required libraries (pyrfc/JCo wrapper, pandas, PyYAML) | Shweta | High | Not Started | Shweta
15 | Infrastructure | SAP NetWeaver RFC SDK / JCo libraries licensed and installed | Required for RFC-based collector connectivity; confirm licensing terms | Shweta | High | Not Started | Shweta
16 | Infrastructure | Network path from collector host to SAP app server validated | Confirm reachability on the SAP gateway/dispatcher port (32xx/33xx) through firewall | Internal IT | High | Not Started | Shweta
17 | Infrastructure | LLM API access provisioned and smoke-tested | API key issued, rate limits understood, and a test call confirmed working before build starts | Rohan | High | Not Started | Rohan
18 | Infrastructure | Secure storage/handling defined for collected data | Encryption at rest, defined retention window, and deletion process for extracted SAP data | Shweta | High | Not Started | Rohan
19 | Compliance / Security | Internal InfoSec sign-off obtained | Confirmation that the collector is read-only and safe to run against a live SAP system | SAP Security SME / Rohan | High | Not Started | Rohan
20 | Compliance / Security | Data handling and retention policy documented | What is collected, where it is stored, for how long, and who can access it | Rohan | High | Not Started | Rohan
21 | Compliance / Security | NDA / data processing agreement template ready | Needed before running the tool against any customer (pilot or otherwise) system | Business/Consulting Lead | Medium | Not Started | Business/Consulting Lead
22 | Compliance / Security | ECS/RISE responsibility matrix validated | Cross-checked against SAP's official RISE service description so SAP-managed items are never scored as customer findings | SAP Security SME | High | Not Started | SAP Security SME
23 | Customer / Pilot Readiness | Customer Basis approval for technical user creation | Required before any pilot/customer engagement can start | Business/Consulting Lead | High | Not Started | Business/Consulting Lead
24 | Customer / Pilot Readiness | Customer security/compliance sign-off to run the assessment | Formal approval that the read-only tool may be run on their landscape | Business/Consulting Lead | High | Not Started | Business/Consulting Lead
25 | Customer / Pilot Readiness | System landscape details confirmed | ECC vs S/4, on-prem vs RISE/private cloud, number of clients/systems in scope | Business/Consulting Lead | High | Not Started | Business/Consulting Lead
26 | Customer / Pilot Readiness | Maintenance window / non-prod system confirmed for pilot run | Preferably run first customer pass on QA/sandbox rather than production | Business/Consulting Lead | Medium | Not Started | Business/Consulting Lead
27 | Documentation / Baseline | Baseline Library v1 finalized and version-controlled | Committed to Git with a version tag before any collector development starts using it | Rohan | High | Not Started | Rohan
28 | Documentation / Baseline | SME sign-off document on baseline thresholds | Written confirmation the maturity thresholds are technically sound | SAP Security SME | High | Not Started | SAP Security SME

## SME Questionnaire
# | Section | Question | Purpose | Priority | Mandatory/Optional | Responsible Person (Customer-side) | Answer / Notes
1 | Current Landscape | How many SAP systems (Dev/QA/Prod) and clients are in scope for this assessment? | Defines collector deployment scope and effort estimate | High | Mandatory | Basis Lead
2 | Current Landscape | What SAP product versions are in use (ECC EhP level, S/4HANA version)? | Determines which baseline entries and collectors apply | High | Mandatory | Basis Lead
3 | Current Landscape | Is the customer on SAP RISE/ECS? If so, which service tier? | Directly determines the ECS/RISE scoring boundary - critical guardrail | High | Mandatory | Basis Lead / Contract Owner
4 | Current Landscape | What is the target S/4 transformation approach (Brownfield/Greenfield/Bluefield) and timeline? | Frames the transformation-readiness scoring context | High | Mandatory | Project Sponsor
5 | Authorization Concept | Is the authorization concept role-based (single/composite/derived roles) or legacy activity-group based? | Baseline for role quality scoring | High | Mandatory | Security Lead
6 | Authorization Concept | What naming convention is used for roles, and is it consistently applied? | Feeds role hygiene sub-score | Medium | Optional | Security Lead
7 | Authorization Concept | Are there SAP_ALL / SAP_NEW assignments in production? To whom, and why? | Critical-authorization risk input | High | Mandatory | Security Lead
8 | Authorization Concept | How frequently are role authorizations reviewed or recertified, and by whom? | Maturity-model input on governance | Medium | Mandatory | Security Lead
9 | Profiles & Parameters | Are RSPARAM/profile parameters centrally managed (RZ10) with change control? | Governance maturity input | Medium | Mandatory | Basis Lead
10 | Profiles & Parameters | Are there known deviations from SAP-recommended security parameters today? | Pre-identifies likely gaps before the collector run | Medium | Optional | Basis Lead
11 | User Management | How are standard users (SAP*, DDIC, EARLYWATCH, TMSADM) managed - locked, passwords changed, monitored? | Standard-user risk scoring | High | Mandatory | Security Lead
12 | User Management | What is the joiner-mover-leaver process for SAP user provisioning/deprovisioning? | Maturity-model input on user lifecycle | Medium | Mandatory | Security Lead
13 | Emergency Access | Is an emergency/firefighter access process in place (SAP GRC EAM or a custom solution)? | Emergency-access maturity scoring | High | Mandatory | GRC Lead
14 | Emergency Access | How are firefighter session logs reviewed, and how often? | Maturity-model input on emergency-access governance | Medium | Optional | GRC Lead
15 | GRC / SoD | Is SAP GRC Access Control implemented? Which modules (ARA, ARQ, EAM, BRM)? | Determines SoD tooling scope and data availability | High | Mandatory | GRC Lead
16 | GRC / SoD | Is there a defined SoD ruleset, and when was it last reviewed? | SoD-readiness scoring input | High | Mandatory | GRC Lead
17 | GRC / SoD | Are SoD violations currently tracked and remediated, or only detected? | Maturity-level distinction (detective vs. corrective control) | Medium | Optional | GRC Lead
18 | RFC Security | How many RFC destinations exist, and are any using stored/hardcoded credentials or trusted/trusting relationships? | RFC hardening scoring input | High | Mandatory | Basis Lead
19 | Gateway Security | Has gateway security (secinfo/reginfo ACLs) been implemented and to what standard? | Gateway hardening scoring input | High | Mandatory | Basis Lead
20 | Audit & Logging | Is the Security Audit Log (SM19/RSAU) active in production, and what is the retention period? | Audit maturity scoring input | Medium | Mandatory | Security Lead
21 | Audit & Logging | Are security logs forwarded to a central SIEM or monitored some other way? | Monitoring maturity scoring input | Medium | Optional | Security Lead
22 | Transport Process | What is the approval process for transporting security-relevant objects (roles, profiles, auth objects)? | Change-control maturity input | Medium | Mandatory | Basis Lead
23 | Fiori / Interfaces | How many Fiori apps/OData services are exposed, and is there a service allowlist? | Interface security scoring input | Medium | Mandatory | Security Lead
24 | Fiori / Interfaces | Are third-party/middleware interfaces (SAP PI/PO, API Management, non-SAP) in scope for this review? | Defines interface inventory and collector scope | Medium | Mandatory | Integration Lead
25 | BTP / Cloud | Is SAP BTP in use, and should it fall within the scope of this assessment? | Scope boundary decision - BTP is out of scope for the current collector set unless confirmed | Medium | Optional | Cloud Architect
26 | RISE / ECS | What does the RISE customer responsibility matrix say for security-relevant parameters, RFC, and OS/DB access? | Directly required to build the ECS-boundary flag correctly - do not proceed without this | High | Mandatory | Contract Owner / Basis Lead
27 | RISE / ECS | Does the customer have direct OS/DB access, or is it fully managed by SAP ECS? | Determines which collectors are technically feasible on this landscape | High | Mandatory | Basis Lead
28 | Custom Developments | Is there a custom authorization-check framework in Z-code (custom AUTHORITY-CHECK usage)? | Custom-code security scoring input | Medium | Optional | Development Lead
29 | Custom Developments | Are there custom RFC-enabled function modules that bypass standard authorization checks? | Critical for RFC hardening completeness | Medium | Optional | Development Lead
30 | Compliance | What regulatory or compliance frameworks apply (SOX, GDPR, industry-specific mandates)? | Adjusts scoring weights and report framing | High | Mandatory | Compliance Officer
31 | Compliance | Are there prior audit findings (internal/external) related to SAP security to factor in? | Avoids duplicating known findings; strengthens report credibility | Medium | Optional | Compliance Officer
32 | Future Roadmap | What is the planned go-live date for the S/4 transformation? | Determines urgency and sequencing of the remediation roadmap | High | Mandatory | Project Sponsor
33 | Future Roadmap | Are there plans to adopt SAP GRC, expand Fiori, or move toward Zero Trust network access post go-live? | Ensures the roadmap aligns with where the landscape is heading, not just where it is today | Low | Optional | Project Sponsor

## Summary Dashboard
Summary Dashboard
Auto-calculated from the other sheets. Nothing to fill in here - just update Status/Owner cells on the other tabs.
Workload by Owner - Daily Task Tracker
Owner | Subtasks Assigned | Total Est. Hours | Completed | % Complete
Rohan | 49 | 136 | 0 | 0%
Shweta | 40 | 141 | 0 | 0%
SAP Security SME | 11 | 27 | 0 | 0%
Business/Consulting Lead | 11 | 30 | 0 | 0%
Total | 111 | 334 | 0
Progress by Phase - Daily Task Tracker
Phase | Subtasks | Total Est. Hours | Completed | % Complete
Phase 0 - Discovery & SME Alignment | 20 | 44 | 0 | 0%
Phase 1 - Baseline Library & Scoring Model Design | 20 | 50 | 0 | 0%
Phase 2 - Collector Script Development | 22 | 77 | 0 | 0%
Phase 3 - Scoring Engine Development | 11 | 40 | 0 | 0%
Phase 4 - AI Reporting & Roadmap Layer | 11 | 38 | 0 | 0%
Phase 5 - Testing (Unit/Integration/Security) | 10 | 34 | 0 | 0%
Phase 6 - Pilot Run & Refinement | 11 | 32 | 0 | 0%
Phase 7 - Productionization & Handover | 6 | 19 | 0 | 0%
Overall Completion by Sheet
Sheet | Total Items | Complete | % Complete
Daily Task Tracker (subtasks) | 111 | 0 | 0%
Prerequisite Checklist | 28 | 0 | 0%
SME Questionnaire (answered = Answer/Notes filled) | 33 | 0 | 0%